## Previous Action Items
Previous Meeting Action Item Status <Date : DD-MMM-YY>
S.No. | Action Items Description | Responsibility | Action taken | Action Created Date | Expected Date of Completion | Actual Date of Completion | Reviewed by | Status | Remarks

## MOM
Minutes of Meeting
Subject :(Project / Function & type of meeting) |  |  | VR Daily Status Meeting |  |  | Date: |  | 2022-11-15
Start Time: |  |  | 05.30 PM |  |  | End Time |  | 06.30 PM
Date of Preparation: |  |  | 2022-11-15 |  |  | Venue: |  | Zoom
Agenda: (Points to be discussed) |  |  | VR Daily Status Meeting |  |  | MOM ID: |  | VR-MOM-219
Participants: |  |  | Karthik,Suganthi,JayaPriya,Sathiyaseelan, Lalit,Aishwarya |  |  | MOM prepared by |  | Sathiyaseelan Ram
Leave or Absence: |  |  | None
Discussion Points/Action Items
Sl. No. | Description | Responsibility | Category | Planned date of completion | Actual date of completion | Reviewed by | Status | Remarks
1 | Carpathian - Insight - Contact Page - Enabled - Add/Edit/Delete Option | Jayapriya Murugan | Action Item | 2022-11-15 |  |  | In progress
2 | TCV - Insight - CR | Suganthi Ravi | Action Item | 2022-11-15 |  |  | In progress
3 | Shreem - IR - ACH - Chase | Lalit Sethi | Action Item | 2022-11-16 |  |  | In progress
4 | Core - DM - Replace Searchable Drop down with IR plugin | Sathiyaseelan Ram | Action Item | 2023-11-22 |  |  | In progress | Estimation, UD and IA are approved in call
5 | Bright - Insight - Document Sub Type CR | Aishwarya N | Action Item | Yet to Decide |  |  | In progress

## Template Change Log
Aspire-Minutes-of-meeting-Template
DOCUMENT NAME: | Aspire-Minutes-of-meeting-Template
DATE: | <February> <19>, <2018>
MODIFICATION HISTORY
PURPOSE OF THE TEMPLATE | This Template can be used to log the minutes of meeting and the action items discussed in any meetings conducted in the projects.
DATE | NAME | CHANGE DESCRIPTION | VERSION
2017-11-06 | Mohanakrishnan | Created the template | 0.1
2018-02-19 | Pradeep Srinivasan & Clara Abraham | Reviewed the template | 0.2
2018-02-19 | Mohanakrishnan | Incorporated the Review comments | 0.3