## Cover Page
Document Name: |  | VR-Shreem IR
Document ID: |  | VR-Shreem IR - Investor Signnow Attributes CR EST-01
Version: |  | 1
Date: |  | 2023-01-02
Modification History
(Kindly remove the modification history of the Template when using this sheet)
Purpose of the Template |  | This template can be used when SMC Estimation
Date | Author |  | Change Description | Version
2023-01-02 | Sathiyaseelan Ramasamy |  | Initial document prepared | 0.1
2023-01-03 | Jayapriya Murugan |  | Document Review | 0.2
2023-01-03 | Sathiyaseelan Ramasamy |  | Updated final version | 1

## Guidelines
Instructions and Guidelines
1 | Define WBS - Identify the scope (use either the activities/deliverables) for the project to define the WBS for your project.
2 | Split the activities/deliverable into task Level
3 | Define the complexity guidelines for the task based on the meaningful parameters (like No. of UI Fields, No. of Transaction, No. of Validation and etc..)
4 | List down the Assumption & Constrains you have considered for the Estimation
5 | List down the technical and delivery related risk which impact on estimation
6 | Identify the internal and external dependencies.
7 | Create the resource loading sheet based on the timeline and estimation agreed with customer.
8 | Create the project plan with identified milestones and dependecines.
9 | Create the project schedule with start and end date for the list of task idenfied in the plan and assign the task to the identified resources.
10 | Baseline the Estimation, Planning and Schdule and get the formal approval.
11 | Re-Estimate the estimation and plan where there is a change in scope.
12 | Get approval and re-baseline the revised estimation, plan and Schedule.

## SMC Definition
SMC Definition - General Guidelines |  |  |  | Complexity Defination (Java)
S.No | Complexity | Effort | Remarks | / Complexity | Simple | Medium | High
1 | Very Simple | 1 day | * Simple UI pages with less than 5 controls with validations with only one db operations | JSP (View) | Few Data entry and display elements and submit points (< 10) | More data entry, display elements and submit points ( < 20 ) Page breaks, display logic, Simple usage of DHTML | Complex Validations, Complex Formatting, Complex page layout, Complex display logic
2 | Simple | 2 days | * Simple UI pages with less than 10 controls with validations * Simple Business logic implementation * DB operations (straight forward Insert, Update and Delete operations)
3 | Medium | 3 Days | * UI pages with less than 10-15 controls and grid/table, with validations * Business logic implementation * DB operations | Servlet (Controller) | 1-2 operations / request. Retrieval and passing of data elements | More operations per request, Session information storing Operations based on servlet session information | Keeping track of processes across pages Request routing based on intermediate operations
4 | Complex | 5 Days | * UI pages with greater than 15 controls and 2 grids/tables, with validations * Medium Business logic implementation * DB operations | EJB (Model) Simple Interface (Few | Simple Interface (Few methods and parameters) Simple data access, data logic (no caching) | Multiple data sources Complex data retrieval and up dation logic Caching | Multiple data sources; involves tables and other sources
5 | Very Complex | 8 Days | * UI pages with greater than 15 controls and multiple grids/tables, with validations * Complex Business logic implementation * DB operations

## Complexity Definition
| Requirement- 10% |  |  |  | Design - 15% |  |  | Coding - 45% | [6 empty] | Testing - 25% |  |  |  |  | Release - 5% |  |  | Total (Hrs)
Complexity | Requirement Gathering | SRS Preparation | SRS Review | SRS Rework | Technical Design Specifications | TDD Review | TDD Rework | View | Business Layer | DAO Layer | Unit Testing | Rework after Unit Testing | Code review | Code Rework | STP / STD Preparation | STD / STP Review & Rework | Functional Testing | Automation Testing | Rework on Testing Comments | Deployment | User Manual | System testing & UAT Support | Total (Hrs) | Total (Days)
| 30% | 50% | 10% | 10% | 80% | 10% | 10% | 25% | 25% | 20% | 10% | 10% | 5% | 5% | 10% | 10% | 30% | 30% | 20% | 20% | 10% | 70%
VS | 0.24 | 0.4 | 0.08 | 0.08 | 0.96 | 0.12 | 0.12 | 0.9 | 0.9 | 0.72 | 0.36 | 0.36 | 0.18 | 0.18 | 0.2 | 0.2 | 0.6 | 0.6 | 0.4 | 0.08 | 0.04 | 0.28 | 8 | 1
S | 0.48 | 1.2 | 0.16 | 0.16 | 1.92 | 0.24 | 0.24 | 1.8 | 1.8 | 1.44 | 0.72 | 0.72 | 0.36 | 0.36 | 0.4 | 0.4 | 1.2 | 1.2 | 0.8 | 0.16 | 0.08 | 0.56 | 16.4 | 2.05
M | 0.72 | 1.2 | 0.24 | 0.24 | 2.88 | 0.36 | 0.24 | 2.7 | 2.7 | 2.16 | 1.08 | 1.08 | 0.54 | 0.54 | 0.6 | 0.6 | 1.8 | 1.8 | 1.2 | 0.24 | 0.12 | 0.84 | 23.88 | 2.985
C | 1.2 | 2 | 0.4 | 0.4 | 4.8 | 0.6 | 0.36 | 4.5 | 4.5 | 3.6 | 1.8 | 1.8 | 0.9 | 0.9 | 1 | 1 | 3 | 3 | 2 | 0.4 | 0.2 | 1.4 | 39.76 | 4.97
VC | 1.92 | 3.2 | 0.64 | 0.64 | 7.68 | 0.96 | 0.96 | 7.2 | 7.2 | 5.76 | 2.88 | 2.88 | 1.44 | 1.44 | 1.6 | 1.6 | 4.8 | 4.8 | 3.2 | 0.64 | 0.32 | 2.24 | 64 | 8
| Days | 1 | 2 | 3 | 5 | 8
| Hrs | 8 | 16 | 24 | 40 | 64
Phase | % | VS | S | M | C | VC
Requirement | 10% | 0.8 | 1.6 | 2.4 | 4 | 6.4
Design | 15% | 1.2 | 2.4 | 3.6 | 6 | 9.6
Coding & Unit Testing | 45% | 3.6 | 7.2 | 10.8 | 18 | 28.8
Testing | 25% | 2 | 4 | 6 | 10 | 16
Deployment & Release | 5% | 0.4 | 0.8 | 1.2 | 2 | 3.2

## Assumption
Assumption
1 | Estimation will be re-visited when ever there is change in scope or technolgoy
2 | The baseline complexity definition is for an average skilled resource on the technology.
3 | Arechitecture & Framewor, Workspace Environment Setup, Performance testing, Deployment, UAT & Warranty support are estimated for the complete application not at individual screen
4 | The technology considered for estimations are IDE - Visual Studio 2008 & above Technology - Microsoft .NET Framework - .NET 4.0, .NET 3.5, .NET 2.0 Application Server - Windows Server 2003 & above Database Server - SQL Server 2008 & above Unit Testing - NA Functional Testing - NA Coding Standards - FxCop Build / Deployment - NA Load / Stress Testing - NA Version Control - SVN Task Tracker - PRISM
5 | This estimation technique would be used for major enhancements. Any work > 40 hours
6
7
8
9
10

## Estimation Sheet
|  |  | Requirement- 10% |  |  |  | Design - 15% |  |  | Coding - 45% | [6 empty] | Testing - 25% |  |  |  |  | Release - 5% |  |  | Total (Hrs)
Sl.No | Screens | Complexity | Requirement Gathering | SRS Preparation | SRS Review | SRS Rework | Technical Design Specifications | TDD Review | TDD Rework | View | Business Layer | DAO Layer | Unit Testing | Rework after Unit Testing | Code review | Code Rework | STP / STD Preparation | STD / STP Review & Rework | Functional Testing | Automation Testing | Rework on Testing Comments | Deployment | User Manual | System testing & UAT Support | Total (Hrs) | Total (Days)
User Entry Columns |  |  | Formula Columns | [21 empty] | 19.68 | 2.46
1 | VR-Shreem IR - Investor Signnow Attributes CR | M | 0 | 0 | 0 | 0 | 2.88 | 0.36 | 0.24 | 2.7 | 2.7 | 2.16 | 1.08 | 1.08 | 0.54 | 0.54 | 0.6 | 0.6 | 1.8 | 0 | 1.2 | 0.24 | 0.12 | 0.84 | 19.68 | 2.46